## Schedule A
Parks Victoria
Contract No. XXXX
Buchan Caves Reserve - North Arm Erosion Mitigation, Drainage & Track Works
Schedule A Price Summary
Schedule | Description | Amount (ex GST)
B1 | Preliminaries | 0
B2 | Erosion Mitgation & Swale Construction | 0
B3 | Track Works | 0
Total (Ex GST) |  | 0
C | Provisional Items | 0
Total including Provisional Items (Ex GST) |  | 0
10% GST |  | 0
Total (Inc GST) |  | 0

## Schedule B1
Parks Victoria
Contract No. XXXX
Buchan Caves Reserve - Erosion Mitigation, Drainage and Track Works
Schedule B1 Schedule of Prices - Preliminaries
Item | Description | Quantity | Unit | Rate | Amount
B1 | Preliminaries
B1.1 | Site establishment and mobilisation including all site facilities & amenities etc. | 1 | Item |  | 0
B1.2 | Prepare and implement management plans (Health & Safety, Environmental Management, Quality Plan and all associated SWMs, JSAs and ITPs) to the satisfaction of the Superintendent | 1 | Item |  | 0
B1.3 | Attendance and participation in kick-off meeting, risk assessment, site induction, cultural awareness training, CHMP awareness training, weekly site meetings | 1 | Item |  | 0
B1.4 | Tree and Asset Protection Works
B1.4.1 | Protection of any vegetation, cultural sites, habitat sites, infrastructure etc that may be affected by the works, to the satisfaction of the Superintendent (may include temporary relocation, removal and reinstatement, etc. as required) | 1 | Item |  | 0
B1.4.2 | Install Tree protection fences and paraweb as per Tree Protection Plan for the duration of the works | 1 | item |  | 0
B1.4.3 | Locate and protect any electrical, plumbing or built assets intended to be kept | 1 | item |  | 0
B1.5 | Supply, installation, and removal of any temporary fencing around construction area, to prevent access by animals and the general public. | 1 | Item |  | 0
B1.6 | Site setout, location of underground services. | 1 | Item |  | 0
B1.7 | Any additional items required for the execution of works in accordance with the drawings and specification not included above. (NB any items priced here must be detailed in an attachment to this Schedule)
B1.7.1 | Tenderer to complete if nominating additional items
B1.7.2 | Tenderer to complete if nominating additional items
B1.7.3 | Tenderer to complete if nominating additional items
| Total Schedule B1 Preliminaries |  | (ex GST) |  | 0

## Schedule B2
Parks Victoria
Contract No. XXXX
Buchan Caves Reserve - North Arm Erosion Mitigation, Drainage & Track Works
Schedule B2 - Erosion Mitigation & Swale Construction
Item | Description | Quantity | Unit | Rate | Amount
B2.1 | Earthworks
B2.1.1 | Clearing of site for safe access to works area | 1 | Item |  | 0
B2.2 | Erosion Mitgiation Works Upstream of Cave Entry (CH 400 - CH 538)
B2.2.1 | Scour Site 1 (Swale Ch 528 - 535). Contractor to fill eroded area with locally sourced fill, reshape stream banks and install Type 2 Filter Material and Rockwork. Extent and scope of works to be agreed with the Superintendent on site | 1 | Item |  | 0
B2.2.2 | Scour Site 2 (Swale Ch 515-520). Contractor to fill eroded area with locally sourced fill, reshape stream banks and install Type 2 Filter Material and Rockwork. Extent and scope of works to be agreed with the Superintendent on site | 1 | Item |  | 0
B2.2.3 | Scour Site 2 (Swale Ch 470-500). Either side of 600mm culverts. Contractor to fill eroded area with locally sourced fill, reshape stream banks and install Type 2 Filter Material and Rockwork. Extent and scope of works to be agreed with the Superintendent on site | 1 | Item |  | 0
B2.2.4 | Other Areas between Ch 400 - 538). Channel improvements as agreed with Superintendent (allowance) | 1 | Item |  | 0
B2.2.5 | At Swale CH 475, Supply and install 1 x 600 dia additional reinforced concrete culvert 5.5m length, install at same invert level as existing. Re-establish track over crossing with 100mm gravel or class 3 crushed rock | 5.5 | lm |  | 0
B2.2.6 | Supply and install rock beaching on geotextile at inlet and outlet of all 3 pipes, as per drawings | 1 | No |  | 0
B2.3 | Demolition and Tree Removal Works
B2.3.1 | Remove and mulch trees identified for removal in the Demolition Plan. Mulch to be retained on site or taken off site as directed by the Superintendent (Approx 27 trees of varying sizes) | 1 | Item |  | 0
B2.3.2 | Remove and dispose offsite any stumps from removed trees, or stumps identified for removal, or otherwise within the construction footprint. | 1 | Item |  | 0
B2.3.3 | Remove and dispose offsite, any redundant infrastructure shown on the Demolition Plan or within the construction footprint. Superintendent shall instruct if any specific items are to be retained for re-use | 1 | Item |  | 0
B2.4 | Swale Drain Construction (CH -14.35 to CH 12.31 (Type 3 Rockwork), including outfall to Spring Creek.
B2.4.1 | Strip all works area of all grass, root growth and topsoil to a depth of up to 100mm and stockpile for reuse. | 215 | m2 |  | 0
B2.4.2 | Excavate Swale Profile to Base of Rock (400mm below FS), sorting spoil into stockpiles: Topsoil, 75mm and larger (for use as beaching), Sand and Gravel (for filter layer), unsuitable material (for offsite disposal) | 100 | m3 |  | 0
B2.4.1 | Win from stockpile and Place Filter Layer (40mm minus, well graded gravel, or crushed rock) - 100mm thick layer | 21.5 | m3 |  | 0
B2.4.2 | Win from stockpile and Place Rock Beaching layer (100-200mm dia rock) - 300mm thick layer | 64.5 | m3 |  | 0
B2.5 | Swale Drain Construction (CH 12.31 to CH 153.4) (Type 2 Rockwork)
B2.5.1 | Strip all works area of all grass, root growth and topsoil to a depth of up to 100mm and stockpile for reuse. | 850 | m2 |  | 0
B2.5.2 | Excavate Swale Profile to Base of Rock (300mm below FS), sorting spoil into stockpiles: Topsoil, 75mm and larger (for use as beaching), Sand and Gravel (for filter layer), unsuitable material (for offsite disposal) | 390 | m3 |  | 0
B2.5.1 | Win from stockpile and Place Filter Layer (40mm minus, well graded gravel, or crushed rock) - 100mm thick layer | 85 | m3 |  | 0
B2.5.2 | Win from stockpile and Place Rock Beaching layer (100-150mm dia rock) - 200mm thick layer | 170 | m3 |  | 0
B2.6 | Swale Drain Construction (CH 153.4 to CH 186.15) (Type 1 Rockwork)
B2.6.1 | Strip all works area of all grass, root growth and topsoil to a depth of up to 100mm and stockpile for reuse. | 206 | m2 |  | 0
B2.6.2 | Excavate Swale Profile to Base of Rock (200mm below FS), sorting spoil into stockpiles: Topsoil, 75mm and larger (for use as beaching), Sand and Gravel (for filter layer), unsuitable material (for offsite disposal) | 80 | m3 |  | 0
B2.6.1 | Win from stockpile and Place Filter Layer (40mm minus, well graded gravel, or crushed rock) - 75mm thick layer | 15.5 | m3 |  | 0
B2.6.2 | Win from stockpile and Place Rock Beaching layer (75-100mm dia rock) - 125mm thick layer | 170 | m3 |  | 0
B2.7 | Swale Drain Construction (CH 186.15 to CH 263.5) (Type 2 Rockwork)
B2.7.1 | Strip all works area of all grass, root growth and topsoil to a depth of up to 100mm and stockpile for reuse. | 503 | m2 |  | 0
B2.7.2 | Excavate Swale Profile to Base of Rock (300mm below FS), sorting spoil into stockpiles: Topsoil, 75mm and larger (for use as beaching), Sand and Gravel (for filter layer), unsuitable material (for offsite disposal) | 230 | m3 |  | 0
B2.7.1 | Win from stockpile and Place Filter Layer (40mm minus, well graded gravel, or crushed rock) - 100mm thick layer | 50.3 | m3 |  | 0
B2.7.2 | Win from stockpile and Place Rock Beaching layer (100-150mm dia rock) - 200mm thick layer | 100.6 | m3 |  | 0
B2.8 | Swale Drain Construction (CH 337.38 to CH 399.1) (Type 2 Rockwork)
B2.8.1 | Strip all works area of all grass, root growth and topsoil to a depth of up to 100mm and stockpile for reuse. | 385 | m2 |  | 0
B2.8.2 | Excavate Swale Profile to Base of Rock (300mm below FS), sorting spoil into stockpiles: Topsoil, 75mm and larger (for use as beaching), Sand and Gravel (for filter layer), unsuitable material (for offsite disposal) | 190 | m3 |  | 0
B2.8.1 | Win from stockpile and Place Filter Layer (40mm minus, well graded gravel, or crushed rock) - 100mm thick layer | 38.5 | m3 |  | 0
B2.8.2 | Win from stockpile and Place Rock Beaching layer (100-150mm dia rock) - 200mm thick layer | 77 | m3 |  | 0
B2.9 | Diversion Bunds
B2.9.1 | Swale Chainage 265 - 280. Diversion bund incorpoarting Track to direct water back into Swale - Win from Stockpile, suitable VicRoads Type B fill, for creating bund. Place in layers to design shape and compact. Adjacent trees on west to be protected. | 44 | m3 |  | 0
B2.9.2 | Swale Chainage 265 - 280. Supply and place 100mm Class 3 Crushed Rock to construct track with (16.8m long x 3.5m wide). | 60 | m2 |  | 0
B2.9.3 | Swale Chainage 265 - 280. Place from Stockpile Type 3 (100-200mm) Rock Beaching along diversion bund face adjacent to swale (allow 35m2 x 300mm deep) | 10.5 | m3 |  | 0
B2.9.4 | Swale Chainage 400 - Adjacent to Cave. Diversion Bund to direct and control cave overflow. Win from Stockpile suitable clay-rich fill for construction of bund. Place and compact in layers to design shape minus 100mm for topsoil | 4 | m3 |  | 0
B2.9.5 | Swale Chainage 400. Win from stockpile and place 100mm topsoil | 17 | m2 |  | 0
B2.9.6 | Swale Chainage 400. Supply and Install jute mat over topsoil | 17 | m2 |  | 0
B2.9.7 | Swale Chainage 530. Bund to prevent water overflowing stream onto track. Win from stockpile suitable clay rich fill for construction of bund. Place and compact in layers to design shape minus 100mm for topsoil | 9 | m3 |  | 0
| Swale Chainage 530. Win from stockpile and place 100mm topsoil | 45 | m2 |  | 0
| Swale Chainage 530. Supply and Install jute mat over topsoil | 45 | m2 |  | 0
B2.10 | Planting - to be carried out in area immediately adjacent to swale and stream, and in upper section of swale batters and stream banks, as agreed with the Superintendent. Planting will require some isolated removal of beaching rock in some locations
Supply and install all tubestock in accordance with the drawings including tree guards where specified.
B2.5.1 | Grasses, Reeds and Sedges in Swale Batters and Steam Banks at Repair Sites, typically between crest and 1m into swale batter, density 2 plants per m2 | 1460 | No |  | 0
B2.5.2 | Small Shrubs, herbs and ferns in the approaches to the stream bank or batter crest. Typically between crest and 1.5m from crest and a density of 2 plants per m2 | 2700 | No |  | 0
B2.5.3 | Maintain for duration of defect liability period (6 months) all landscape works including watering, weeding (eradication), mulch (top up), fertilise, maintain stakes and ties, plant replacements. Note that plant replacements required due to theft are excluded, and dates of theft and photographic evidence must be provided to substantiate that theft has occured. | 1 | Item |  | 0
B2.6 | Site clean up on completion of works. | 1 | Item |  | 0
B2.7 | Any additional items required for the execution of works in accordance with the drawings and specification not included above. (NB any items priced here must be detailed in an attachment to this Schedule)
B2.7.1 | Tenderer to complete if nominating additional items
B2.7.2 | Tenderer to complete if nominating additional items
Total Schedule B2 - Erosion Mitgation & Drainage Works |  |  | (ex GST) |  | 0

## Schedule B3
Parks Victoria
Contract No. XXXX
Buchan Caves Reserve - North Arm Erosion Mitigation, Drainage & Track Works
Schedule B3 - Track Works
Item | Description | Quantity | Unit | Rate | Amount
B3.1 | Earthworks - Most of the new track is built directly on top of the old track, with an additional turning area and an extension to the culvert crossing
B3.1.1 | Strip all cut and fill areas of all grass, root growth and topsoil to a depth of 200mm and stockpile for use. (300m2 for road extension, 150m2 for turning area) | 450 | m2 |  | 0
B3.1.2 | Reshape existing track sub-base / subgrade to promote drainage toward the swale or stream, ensure all areas will free-drain when final track surface is placed. | 1 | Item |  | 0
B3.2 | Track Construction
B3.2.1 | Excavate for pavement subgrade. Allow to dispose of excess material from the site. (Estimated quantity) | 150 | m3 |  | 0
B3.2.2 | Proof Roll sub-base / subgrade. Repairs if required to be treated as variation | 1 | Item |  | 0
B3.2.3 | Supply and install 3.5m wide, 200mm depth (Class 3) Crushed Rock access track, including turning area and track extension | 1400 | m2 |  | 0
B3.2.4 | Supply and install 150mm dia Treated Pine bollards and lockable chain at track termination - location to be advised by Superintendent | 6 | No |  | 0
B3.3 | Any additional items required for the execution of works in accordance with the drawings and specification not included above. (NB any items priced here must be detailed in an attachment to this Schedule)
B3.3.1 | Tenderer to complete if nominating additional items
B3.3.2 | Tenderer to complete if nominating additional items
Total Schedule B3 - Track Works |  |  | (ex GST) |  | 0

## Schedule C
Parks Victoria
Contract No. XXXX
Buchan Caves Reserve - North Arm Erosion Mitigation, Drainage & Track Works
Schedule C - Provisional Items
Item | Description | Quantity | Unit | Rate | Amount
C1 | Supply Only - Filter Material (40mm minus, well graded gravel or crushed rock). To be supplied to suppliment material sorted from excavation in Schedule B2) * | 260 | m3 |  | 0
C2 | Supply Only - Beaching Rock (75-100mm diameter, for Type 1 Swale Lining). To be supplied to suppliment material sorted from excavation in Schedule B2) * | 20 | m3 |  | 0
C3 | Supply Only - Beaching Rock (100-200mm diameter, for Type 2 and 3 Swale Lining). To be supplied to suppliment material sorted from excavation in Schedule B2) * | 520 | m3 |  | 0
C4 | Supply and place additional rock beaching | 60 | m3 |  | 0
C5 | Supply and place additional geofabric | 100 | m2 |  | 0
C6 | Supply and place additional Class 3 CR | 35 | m3 |  | 0
C7 | Nom. CH 300 construct culvert under existing track
C7.1 | Supply and install 300 dia culvert (4.8m length) | 4.8 | Item |  | 0
C7.2 | Supply and install 300 dia endwalls | 2 | No |  | 0
C5 | Nom. CH 100 Supply and install culvert to transfer building drainage to east side of track
C5.1 | Supply and install trafficable grated pit / JP (nom. 600 x 600) | 1 | Item |  | 0
C5.1 | Supply and install 300 dia culvert (4.8m length) | 4.8 | m |  | 0
C5.2 | Supply and install 300 dia endwall | 1 | No |  | 0
C6 | Dayworks (including relocation / lowering of services if required) | 1 | No |  | 0
C7 | Any additional items required for the execution of works in accordance with the drawings and specification not included above. (NB any items priced here must be detailed in an attachment to this Schedule)
C7.1 | Tenderer to complete if nominating additional items
C7.2 | Tenderer to complete if nominating additional items
Total Schedule C - Provisional Items |  |  | (ex GST) |  | 0
* - Provisional Quantity assumes that 25% of the total required material volume will be sourced from excavated material and 75% will be supplied by the Contractor for an extenal source. Externally supplied Rock Beaching shall be similar in colour and shape to existing stream bed rocks, to the extent possible

## Schedule D
Parks Victoria
Contract No. XXXX
Buchan Caves Reserve - North Arm Erosion Mitigation, Drainage & Track Works
Schedule D - Plant & Day Rates
Item | Resource | Name | Rate/hr
Personnel
1 | Project Director
2 | Project Manager
3 | Site Manager / Supervisor
4 | Foreman
5 | Labourer
6 | Other
List Major Plant
8
9
10
11
12
Any specialty plant to be hired for works
13
14
15
16
17